## Wave 23 - Plan
[5 empty] | Data Science | [8 empty] | Development(Front End) | [5 empty] | Common (Sessions - For All)
Ahmed | Loay | Dima | Fatmah | NO | Stage | Duration(Working Days) | Person | Assignment | Resource/Instructor |  | Mohamed | Doha | NO | Stage | Duration(Working Days) | Person | Assignment | Resource/Instructor | NO | Stage | Duration(Working Days) | Person | Assignment | Resource/Instructor | Ahmed | Dima | Fatmah | Doha | Loay | Mustafa | Mark | Islam
|  |  |  | DS1 | Python | 3 | Sohayb |  | Sohayb |  |  |  | FE1 | Html/Css | 20 | Amen | FE1 | FE1 | C1 | Commands Line | 1 day | Fawzy | n | Fawzy
|  |  |  | DS2 | x | 1 | Fawzy | Course follow up | Product management in datascience |  |  |  | FE2 | Bootstrap, Font,,, |  | Amen | FE1 | FE2 | C2 | Basic Backend | 3 days | Emad |  | Emad
|  |  |  | DS3 | Professional Excel | 2 | Fawzy | Data Cleaning & Preprocessing | ITI resources |  |  |  | FE3 | Preprocessor |  | Nabil | FE1 | FE2 | C3 | Git | 1 day | [Intermediat]
|  |  |  | DS4 | Professional Power BI | 3 | Fawzy | Data Visualization | ITI resources |  |  |  | FE4 | Javascript | 20 | Emad |  |  | C4 | App level | 2 days | Emad |  | Emad
|  |  |  | DS5 | Python for data cleaning and preprocessing |  | Mgharbel | Data cleaning and visualization project | Fawzy |  |  |  | FE5 | Typesscript |  |  |  |  | C5 | Docker |  | Emad
|  |  |  | DS6 | Math - ML | 18 | [6 empty] | FE6 | Brwoser, Browser API |  |  |  |  | C6 | Basics DB |  | [Data Science]
|  |  |  | DS7 | Computer vision | 18 | [6 empty] | FE7 | Framework(React/Angular) | 20 | Nabil
|  |  |  | DS8 | NLP | 18
[13 empty] | FE8 | Accessibility | 20 | [Intermediate]
[8 empty] | Final project |  |  |  |  | FE9 | UX |  | Ali
[13 empty] | FE10 | SEO |  | Emad
[13 empty] | FE11 | PWA |  | [Intermediate]
[14 empty] | SSR,,, |  | [Intermediate]
[14 empty] | Mobile |  | Tamer/Ziad
Development(Backend C#)
[9 empty] | Mustafa | Mark | Islam | Loay | NO | Stage | Time(Working Days) | Person | Assignment | Resource/Instructor
[13 empty] | BECS1 | C# | 20 |  |  | BECS1
[13 empty] | BECS2 | Basics DBMS | 5 |  |  | BECS2
[13 empty] | BECS3 | Linq | 5 |  |  | BECS3
[13 empty] | BECS4 | Entity frawwork | 10 |  |  | BECS4
[13 empty] | BECS5 | Dot net core API | 20 |  |  | BECS5
[13 empty] | BECS6 | Dot net core MVC | 5 |  |  | BECS5
[13 empty] | BECS7 | Idntity | 10 |  |  | BECS5

## Current Stage - Data Science
Month of Feb
Week 1 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
| Python |  | Sohayb |  | Sohayb
Week 2 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday 12-2 | Data Science in Business | Data types with examples | Fawzy
Monday 13-2 | Data warehousing | Data warehousing | Fawzy
Tuesday 14-2 | Introduction to DS Tools (Excel) | Practicing Excel AGG functions | Fawzy | Central bank data
Wednesday 15-2 | Practicing Excel AGG functions | Pivot tables using Excel | Fawzy
Thursday 16-2 | Data cleaning using excel (Project) | Data cleaning using excel (Project) | Fawzy | HTTP LOGS
Week 3 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday 19-2 | Introduction to Power BI | Practicing Power BI's Functions
Monday 20-2 | Dax scripting | Data cleaning using Power BI |  |  | Fawzy
Tuesday 21-2
Wednesday 22-2
Thursday 23-2
Week 4 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday
Monday
Tuesday
Wednesday
Thursday

## Current Stage - Development
Month of Feb
Week 1 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
| Html/Css |  | Ameen
Week 2 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday 12-2 | Html/Css |  | Ameen
Monday 13-2 | Html/Css |  | Ameen
Tuesday 14-2 | Html/Css |  | Ameen
Wednesday 15-2 | Html/Css |  | Ameen
Thursday 16-2 | Html/Css |  | Ameen
Week 3 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday 19-2 | Html/Css |  | Ameen
Monday 20-2 | Html/Css |  | Ameen
Tuesday 21-2 | Html/Css |  | Ameen
Wednesday 22-2 | Html/Css |  | Ameen
Thursday 23-2 | Html/Css |  | Ameen
Week 4 | Period 1 | Period 2 | Person | Assignment | Resource/Instructor
Sunday | Bootstrap, Fonts,,, |  | Ameen
Monday | Bootstrap, Fonts,,, |  | Ameen
Tuesday | Preprocessor |  | Ameen
Wednesday | Preprocessor |  | Ameen
Thursday | Preprocessor |  | Ameen